## MAS draft metric driver diagram
Driver Diagram – NAD MAS Draft Healthcare Quality Improvement Plan 2026 (initial)
Draft metrics associated with the five key project Goals set out below. These metrics and associated drivers are subject to change based on assessments of feasibility and data quality
1 | Aim | Primary Drivers | Secondary Drivers | Change Ideas
| Project Goal | We need to ensure | Which requires
|  | Dates of referral and diagnosis are clearly recorded | Services require consistent monitoring outputs to assure themselves of their targets and performance | Pathway mapping exercises including review of all waiting lists at each point in the pathway
| Waiting time: | Systems are capable of reporting in a timely and ongoing way | Trust Management support allocated time to pathway review and reporting development
| •To reduce the average overall waiting time from referral to diagnosis, measured as the time between recorded date of referral and recorded date of diagnosis | Pinch points or bottlenecks are clearly identified through staff review | Review of the pathway is prioritised and time allocated | Triage review to ensure that all elements of assessment are necessary and appropriate to each patient. E.g. brain scan, OT assessment
|  | Feedback from service users and carers is regularly collated and discussed | Systems and reporting support analysis of the data showing breakdown by locality and demographics | Review of model and staff input at each point
|  | Importance of equity of access is understood | Commissioners require evidenced assurance of equitable access
|  |  | Joint working with primary care and other specialities | Consultation with service users about pre-assessment and assessment access – telephone triage, home visits etc
|  |  | There is regular PREM data collection and other opportunities to provide feedback | Consultation with staff about service model, delays and inputs
2 | Aim | Primary Drivers | Secondary Drivers | Change Ideas
| Project Goal | We need to ensure | Which requires
|  | ongoing audit of availability/ access to PACS by MAS | Services require consistent monitoring outputs to assure themselves of their targets and performance | Ensuring staff are informed and trained
| Neuroimaging: | Understanding of the need to access PACS directly to improve diagnosis and cut waiting times | Trust Management support quality improvement and joint working | Collating information on and presenting breakdown of waiting times, including any additional time to access scan resutls
| Increase the proportion of services with access to Picture Archiving and Communication System (PACS) | Importance of equity of provision is understood | Systems and reporting support analysis of the data showing breakdown by locality and demographics | Consultation with staff about service model, delays and inputs
Commissioners require evidenced assurance of equitable provision
Clear communication with primary care and other specialities
Joint working with primary care and other specialities
3 | Aim | Primary Drivers | Secondary Drivers | Change Ideas
| Project Goal | We need to ensure | Which requires
|  | Specific diagnoses are clearly recorded and coded | Services require consistent monitoring outputs to assure themselves of their targets and performance | Consultation with staff about how diagnosis is recorded
| Diagnosis and variation: | Systems are capable of reporting in a timely and ongoing way | Trust Management support training and support for diagnostic reporting | Joint working between services comparing rerecording in different parts of the system
| Decrease the variation between services in reporting diagnosis by dementia type | Systems are accessible, easy to use and comparable in output | Systems and reporting support analysis of the data showing breakdown by locality and demographics | Trust level working with in house data analysts to identify issues
|  |  | Commissioners require evidenced assurance of equitable access | Outliers (in proportion shown by breakdown of diagnoses) to be clearly identified by audit, information fed back to services
|  | Importance of equity of provision is understood | Clear communication with primary care and other specialities | Development of clear training and information about system usage
|  |  | Joint working with primary care and other specialities | Collaboration with researchers
4 | Aim | Primary Drivers | Secondary Drivers | Change Ideas
| Project Goal | We need to ensure | Which requires
|  | Referral for CST and associated diagnosis are clearly recorded | Services require consistent monitoring outputs to assure themselves of their targets and performance
| CST provision: | Systems are capable of reporting in a timely and ongoing way | Systems and reporting support analysis of the data showing breakdown by locality and demographics | Review of service provision and barriers to access
| Increase the proportion of patients receiving Cognitive Stimulation Therapy (CST) | Monitoring and review includes referral to third sector providers | Commissioners prioritise interventions recommended by NICE and require evidenced assurance of equitable provision | Whole Trust review of provision, availability and equality of access
|  | Feedback from service users and carers is regularly collated and discussed | Joint working with primary care and other specialities | Consultation with service users about the quality of therapy received, barriers to access
|  | Importance of equity of provision is understood | There is regular PREM data collection and other opportunities to provide feedback | Staff training and information provision on CST benefits
There is understanding of the benefit and necessity of CST
5 | Aim | Primary Drivers | Secondary Drivers | Change Ideas
| Project Goal | We need to ensure | Which requires
|  | Each patient has a personalised care plan which details support, treatment and other interventions, and monitoring, which is discussed and agreed by the person and healthcare professionals. | Care plans are clearly defined and staff work with people with dementia and their carers to complete and update them | Elements of post diagnostic support are clearly defined and communicated to service users
| Post diagnostic monitoring: | There is regular monitoring and review of care plans including post diagnosis | Systems and reporting support analysis of the data showing breakdown by locality and demographics | Review of service provision and barriers to access
| Increase the proportion of patients receiving post diagnostic monitoring | Monitoring and review includes referral to third sector providers | Commissioners prioritise interventions recommended by NICE and require evidenced assurance of equitable provision | Whole Trust review of care planning and inputs, ties to pathway review
|  | Feedback from service users and carers is regularly collated and discussed | Joint working with primary care and other specialities | Consultation with service users about the quality of care plans, information and communication
|  | Importance of equity of provision is understood | There is regular PREM data collection and other opportunities to provide feedback | Staff training and information provision of care planning
Systems adapted to support easy care plan updates